{"text_format":"3","workbook":"xlsx","n_sheets":2,"sheets":["Sheet2","Sheet3"],"read":"whole","date_system":"1900"}

{"sheet":"Sheet2","index":0,"n_rows":11,"n_cols":4,"rows_kept":11,"merged":[[1,0,1,3],[3,0,6,0],[7,0,8,0],[9,0,9,3]]}
["附件5"]
["小型水库除险加固攻坚行动目标完成情况责任追究及激励约束标准"]
["攻坚目标任务","进度控制指标","责任追究及激励措施","监督单位"]
["攻坚解决在建项目遗留问题","年度目标完成低于60%","1.对责任单位和责任人通报到省，在全国水利建设市场监管服务平台公示\n2.约谈省级水行政主管部门主要负责人\n3.作为激励约束的负面因素\n4.作为水利建设质量工作考核内容\n5.对责任单位和市场主体及其负责人进行责任追究","水利部"]
[null,"年度目标完成高于60%低于80%（含60%）","1.在行业内对责任单位和责任人进行通报，在全国水利建设市场监管服务平台公示\n2.约谈省级水行政主管部门相关负责人\n3.作为激励约束的负面因素\n4.作为水利建设质量工作考核内容\n5.对责任单位和市场主体及其负责人进行责任追究","流域管理机构"]
[null,"年度目标完成高于80%低于100%（含80%）","1.省级水行政主管部门约谈地方相关负责人，约谈情况报水利部\n2.省级水行政主管部门对责任单位和市场主体及其负责人进行责任追究","省级水行政主管部门"]
[null,"年度目标完成超过100%","作为激励因素","水利部、\n省级水行政主管部门"]
["攻坚完成待实施项目建设任务","年度目标完成低于80%","1.对责任单位和责任人通报到省，在全国水利建设市场监管服务平台公示\n2.约谈省级水行政主管部门主要负责人\n3.作为激励约束的负面因素\n4.作为水利建设质量工作考核内容\n5.对责任单位和市场主体及其负责人进行责任追究","水利部"]
[null,"年度目标完成高于80%低于100%（含80%）","1.省级水行政主管部门约谈地方相关负责人，约谈情况报水利部\n2.省级水行政主管部门对责任单位和市场主体及其负责人进行责任追究","流域管理机构"]
["备注：1.依据中华人民共和国行政处罚法、中华人民共和国国水法，水库大坝安全管理条例，水利部颁布的规章、规范性文件等；\n      2.责任追究和激励约束按省级月度、流域管理机构季度、水利部年度进行攻坚行动进度节点控制。        "]
["  "]

{"sheet":"Sheet3","index":1,"n_rows":0,"n_cols":0,"rows_kept":0}